## General Development
General Policies for Code
Write a CPU and GPU version for all functionality.
Write Matlab for all functionality, if it doesn't yet exist.
Directory tree? For example keep input images under /Images Code should access them there. Output images can be where build is done.
Testing?
Documentation?
End of phase review by team.
Pass float *data as the image is transformed. It should eventually be an int of somekind before writing to file.
Compressed data doesn't need to be pixel value. It could be just a mapping back to a pixel value.
Must have makefile. Could have MSVC for windows.
Build for 1.1, 2.0, and 3.0 capabilities/.
Assignments
When you finish a task, select another from the list and put your name on it and check it back in.
Update status after milestones.
We are expected to finish a phase, and keep this on a branch tag, before going onto a new phase.
Open issues
Which pieces run on host?
What granularity of API do we want to supply for Octave?
Should we use doxygen?
Is CUDA both C and C++? Can we use classes?

## Phase1
PHASE 1
| Parameters: | Phase 1 is to complete this for a tile
Wavelet will be Haar.
| sizeOfTile | It is square. | Quantization will be uniform or log.
| numSteps |  | Encode will be run length encoding
| cutoff |  | We can come up with the format we want for the compressed image.
| bits |  |  | The header needs to hold everything associated with the tile that is needed to reconstruct.
Report comparision beteen CPU and GPU
Report error of reconstruction.
Docs | Tests | Status | Who | Task
|  | Working | Ed | Wavelet transform
|  | Working | Ed | Inverse wavelet transform
|  | Working | David | Call CUDA from Octave
|  | C++ cdded. Some GPU code. Still testing. | Bonnie | Threshold
|  | C++ coded. Some GPU code. Still testing | Bonnie | Quantization, uniform and log
|  | Partial implementation | Bonnie | De-quantization, uniform and log
|  |  | Ed | Run Length Encoding
|  |  | Ed | Run Lendth Decoding
|  |  | Ed | Entropy encoding
|  |  | Ed | Entropy decoding
|  |  | Ed | Writing file with header
|  |  | Ed | Reading file with header
|  |  | Ed | Report Comparison between CPU and GPU
Report Comparison between original and reconstructed
Finding compelling images
Writing abstract
Forward compression with quantization selection
Reverse compression with quantization selection
Unit Tests policies
Integration test policies
Doxygen generation
Write unit tests
Write integration tests

## Phase 2
PHASE 2
The main activity in phase 2 is to replace cutoff with an acceptable error and number of bits.
We will use the definition of error to be the difference in the energy of the image, in order to convert from acceptable error to cutoff and output bits..
Energy of an image is the sum of the squares of pixel values.
Parameters:
Wavelet will be Haar.
| sizeOfTile | It is square. | Quantization will be uniform or log.
| numSteps |  | Encode will be run length encoding
| acceptable error |  | Same file format
| bits |  | Report comparision beteen CPU and GPU
Report error of reconstruction.
Report error of reconstruction in terms of energy and mean square pixel delta.
Docs | Tests | Status | Who | Task
Figure out the details of number of bits
Change error reporting to be in terms of Energy
Add versions of tests to use acceptable error rather than cutoff

## Phase 3
PHASE 3
The main activity in Phase 3 is 1) tiling larger images,2)implementing the CFD 9,7 wavelet, and 3)implementing codebook based quantization.
Parameters:
Wavelet will be Haar or CFD 97 wavelet.
|  | sizeOfTile | It is square. | Quantization will be log.
|  | numSteps |  | Encode will be run length encoding
|  | acceptable error |  | Same file format
|  | bits |  | Report comparision beteen CPU and GPU
Report error of reconstruction.
Report error of reconstruction in terms of energy and mean square pixel delta.
Docs | Tests | Status | Who | Task
Decide what takes place on host versus what is done by GPU
|  |  | David | Implement a codebook quantization (lloyd's)
|  |  | David | Implement codebook based dequanization (lloyd's)
Make type of quantization selectable in interfaces
Design data associated with each tile and that needs to persistent in order to decompress. Class instance?
Design new file format to take tile headers into account.
Design new file format to put codebooks into tile headers.
Update write compressed file
Update read compressed file
Tests for codebook quantization
Tests for Tiling

## Phase 4
PHASE 4
The main emphasis for Phase 4 is 3D compression
Parameters:
Wavelet will be Haar or CFD 97 wavelet.
| sizeOfTile | It is square. | Quantization will be uniform, log, or codebook based.
| numSteps |  | Encode will be run length encoding
| acceptable error |  | File format changed to specify which wavelet in header
| input bits |  | Report comparision beteen CPU and GPU
| output bits |  | Report error of reconstruction in terms of energy and mean square pixel delta.
Docs | Tests | Status | Who | Task

## Non-code Tasks
Date | Who | Task
Finding test images
Finding compelling images for the conference
Writing the abstract
| Sergio | Writing the paper.
Defining the Octave API